## Slide 1
Results-Based Management (RBM) approach Presentation for Intangible Cultural Heritage Category 2 Institutes
“A nation is alive as long as its culture is alive”
Bureau of Strategic Planning
2013

## Slide 2: Results-Based Management (RBM)
Pillar of the UN Reform
UNESCO Reform
“RBM is a participatory and team-based approach to management designed to improve programme delivery and management effectiveness, efficiency and accountability that focuses on achieving defined results, and should be applied in all stages of programming.”
BSP: 36 C/5
The RBM approach entails:
  - Emphasis on results.
  - Shifting the focus from how things are done to what is accomplished.
BBM
OBM
PBM
RBM
Notes: 2
1. The Results-Based Management approach (RBM) was introduced to the United Nations system as part of the reform process. In the “Programme for Reform” presented to the General Assembly in 1997, the then Secretary-General proposed: “that Member States and he enter into a dialogue with the aim of shifting the United Nations programme budget from a system of input accounting to results-based accountability. Under this new approach [...] the General Assembly, through its relevant Committees, would specify the results they expect the Organisation to achieve within the relevant budgetary constraints. The secretariat would be held responsible for, and judged by, the extent to which the specified results are achieved.”
In 1999, UNESCO’s Director-General M. Koshiro Matsuura, emphasized the importance of pushing forward the RBM agenda (Speech of the Director-General at the closing ceremony of the 30th session of UNESCO’s General Conference Wednesday 17 November 1999). Hence, applying the UN decision was rather quick, which was most probably due to the fact that it was particularly pertinent for UNESCO who is the only UN Specialised Agency/Fund/Programme which has 5 mandates. At the time, (and some say still today in certain areas) we worked in silos and RBM was seen as a new management approach which would favour working in an intersectoral (and intrasectoral) manner, thus ensuring that our comparative advantage (pulling expertise from all five areas of competence to tackle issues faced by the world population) would be fully put to practice for the benefit of the Member States. Working/programming in term of results facilitates intersectoral cooperation, as when you discuss in terms of change all experts can determine how to contribute to obtain the intended change, whereas when you discuss in terms of what you want to do (interventions/outputs/deliverables), it is more difficult for others than the ones organising to find entry points for contribution. This is even more difficult when you discuss in terms of budget required. At the end of the discussion it might turn out that a complete new set of interventions, outputs/deliverables and budgets required will be determined (e.g. the major world conference might not be the best output/deliverable to attain the result).
2. Results-Based Management is a participatory and team-based approach to Management designed to improve delivery programme and management effectiveness, efficiency and accountability that focuses on achieving defined results, and should be applied at all stages of programming.
This approach integrates implementation strategy, people, and resources, through measurements to improve decision making, transparency and accountability. It focuses on the definition of results via a situation analysis, a stakeholder analysis and a resource analysis. It is essential to first specify the needs to be answered, analyze who will benefit from your intervention and with whom you will be working, taking into account the resources available in order to define the results to be attained. This process will carry out improvements in decision-making, transparency and accountability as Responsible Officers will have full knowledge of the facts. Well-defined results will improve the performance of the Organization.
3. Hence, in line with the UN reform, UNESCO has shifted from a Budget-Based Management approach (BBM), with main focus on how the budgets were programmed and spent, to Project-Based Management (PBM), with main focus on how it will and has been done to a Results-Based Management approach (RBM) with main focus on programming and attainment of results.
4. The Results-Based Management approach entails placing greater emphasis on results in its programming, budgeting, management, monitoring, reporting and evaluation and replacing the focus from how things are done to what is accomplished.
- RBM focuses on the change. What do we want our beneficiaries to do differently?
- RBM favours teamwork and a participatory approach; it is a human approach. It is a technique not a magic wand which will solve all issues.
- RBM is applied to all Programme Sectors and Programme-related and Corporate Services.

## Slide 3: UNESCO Programme Management Framework

## Slide 4: The 34 C/4, the 35 C/5 and 36 C/5
BSP: 36 C/5
Mission statement
Overarching Objectives
Strategic Programme Objectives
Global Priority Africa and
Global Priority Gender Equality
34 C/4 (2008-2013)
Intersectoral Platforms
35 C/5 – 36 C/5
Major Programme
Biennial Sectoral Priority
Main Line of Action
Grouping
Activity/Extrabudgetary project/Office 5
- Result
- Thematic/Regional
Notes: 4

## Slide 5: RBM: The transformative process/ intervention logic
Input: available resources
Intervention: act to be undertaken
Output/deliverable: first effect which contributes to attaining the result
Result: change
BSP: 36 C/5
Issue to be tackled:
Economic difficulty
Group Work 1
Notes: 5
1. Hence, at the heart of the RBM approach is the transformative process or intervention logic, where the different notions (i.e. input, intervention, output/deliverable and result) of RBM come together.
2. Imagine a village in Africa where aged villagers have artistic skills transmitted by their ancestors. The village is encountering economic difficulties and young villagers who do not have the artistic skills are not producing the arts crafts.
UNESCO is going to intervene in order to assist the villagers in improving their living conditions through its arts crafts network. UNESCO experts will gather the villagers, including the religious leader and chief to convince the villagers that they can benefit from the “new knowledge” or artistic skills to improve their living conditions. UNESCO will organise training to disseminate knowledge. The Organization will also finance and elaborate a booklet with pictures, with the participation of aged villagers to disseminate the knowledge to young generations. Under the aegis of UNESCO, a local association will be created gathering the villagers who have acquired the artistic skills. This association will be part of a wider network of crafts associations. The association will follow the standards established for the production of arts crafts goods. Each arts crafts will have the UNESCO label proving the seal of excellence. UNESCO with its stakeholders will assist the association to increase its visibility though arts craft sales in markets. Thanks to the increase of income, the villagers will improve considerably their living conditions and preserve their cultural identity.
- The input represents the expertise of UNESCO that is the staff; the financial resources they will allocate to the training; the booklet (if previously existing and requiring adaptation to specific context).
- The interventions will be the meeting with the villagers and the chief of village; the organisation of training.
- The outputs/deliverables will be the training undertaken; the booklet produced (if new); the association created.
- The results: short to medium-term result: Association follow the standards; Young generation villagers produce and sell the craft products; medium to long-term result better living conditions for the villagers; cultural identity protected and preserved.
This being said all including outputs/deliverables are required to attain the result. Hence, RBM does not oppose the output/deliverable and the result rather it favours to go beyond the output/deliverable step ensuring that all actions possible are undertaken to ensure that a change occurs for the beneficiary group. Hence, RBM changes the focus from the output/deliverable produced by UNESCO to the change for the beneficiaries responding to the question: what for, what is the finality of the activity/project/programme for the beneficiary group?
3. Due to UNESCO’s line of work and its five functions, most activities/projects/programmes involve raising awareness, development of knowledge or capacity building of skills and providing technical advice.
To ensure that the knowledge or skills are used as intended by the beneficiaries, it is important to clearly define the roles and responsibilities of all stakeholders concerned and to obtain their commitment. This is a way to ensure that we move from the output/deliverable to the result; that our stakeholders take measures to attain the result.
- Majority of activities/projects which fail are due to the fact that the roles and responsibilities of stakeholders are not properly defined and agreed upon. Yet it is thanks to this component that the result formulation will be defined as it will respond to “what are the beneficiary groups to do differently after UNESCO’s action”. Furthermore, it allows putting back a bit more of control as it identifies all stakeholders and their roles. As such, it also minimises the risk for misunderstandings as all parties need to agree on it. If you stakeholder acts both as a beneficiary group and a partner, ensure that you precisely describe both roles and responsibilities.
- Defining roles and responsibilities through our example:
Aged villagers have artistic skills transmitted by their ancestors. They agree to transfer this knowledge to the young villagers. On their side, young villagers agree to be trained and to use the new knowledge of artistic skills. All villagers agree to participate actively in the local association of art crafts managed by UNESCO to disseminate local skills. They will benefit from UNESCO’s name to have access to places to sell their goods and increase their income. The whole village will benefit from the protection and preservation of local culture for future generations.
4. Independently of the programmatic level, all Responsible Officers and their teams need to go through this process.

## Slide 6: Results-Based Management (RBM) The “transformative process”
New knowledge and dissemination:
Ex1: Establishment of the local association on crafts to disseminate the artistic products to the public at large.
Capacity-building of stakeholders directly involved:
Ex1: UNESCO, the aged villagers, network of local association, newly trained villagers.
Roles and responsibilities:
Ex1: as a beneficiary: the members of the local association are informed by the exchange of experiences of the various stakeholders regarding the network of local association.
Ex2: as a partner: the local association will apply the standards established for the production of crafts goods.
Notes: - Accountability (shared responsibility among the Organization, partners and beneficiaries)
- Are all parties equally responsible for success as for failure?
- Mutual agreement on roles and responsibility

## Slide 7
Programming framework

## Slide 8: Programming framework
Where do you stand?
  Identification of the contribution to upstream result(s) (a prerequisite)
Where do you start?
  Assessment of the issues to be addressed
  Identification of stakeholders involved and concerned
  Estimation of resources available
What are you going to achieve?
  Formulation of results to be attained
  Definition of measurable indicators
How are you going to proceed?
  Development of a strategy for implementation and attainment of results

## Slide 9: Results framework/chain Identification of the contribution to outcomes of C/4 and expected results of C/5
Overarching Objectives (Expected outcomes)
Strategic Programme Objectives (Expected outcomes)
Major Programme
Biennial Sectoral Priority
Main line of Action (Expected results)
Grouping
Activity/Extrabudgetary project (Expected results)
C/4 Medium-Term Strategy
C/5 Programme and Budget
Workplans

## Slide 10: Situation analysis Assessing the issues to be addressed
Analysis of the situation prevailing before the intervention in order to identify the issues (and baseline) to be addressed within UNESCO’s areas of competence.
What is the current situation in the field of your work (the situation by the end of previous biennium)?
What are the key issues to be addressed during the next two years (and within the longer-term framework)?
What could be done differently to improve the future performance, based on the experience of the past?

## Slide 11: Situation analysis Elements to be considered
BSP: 36 C/5
The human-rights based approach, including gender equality to avoid perpetuating inequalities
Risk management to obtain the most realistic planning
Geographical scope: global or by region(s), by sub-region(s) or by country to determine the geographical zone that will benefit from the activity
The Stakeholders: the target groups and the partners to define specifically the role and responsibility of the direct beneficiaries and partners involved
The financial and human resources to estimate what is necessary in terms of budget and team
Notes: 11
Human-Rights Based Approach (HRBA):
- The capacity of rights-holders to claim their rights
- The capacity of duty-bearers to fulfil their obligations
Gender Equality at the heart of HRBA:
- Women’s empowerment
- Gender mainstreaming
Identification of responsibilities and capacity-gaps:
- For duty bearers to fulfil their obligations to ensure that rights can be exercised
For right holders to claim and exercise their rights
For Women and Men to have equal opportunities
Risk Management:
- A risk is an uncertain event that may impact the performance of the programme delivery either positively or negatively
- Undertaking a systematic risk analysis throughout all processes of RBM enables you to improve programme design
- It informs decision-making and facilitates the establishment of preventive measures in order to manage the risks and mitigate their negative impact
Accountability (shared responsibility among the Organization, partners and beneficiaries)
- Are all parties equally responsible for success as for failure?
- Mutual agreement on roles and responsibility

## Slide 12
Situation analysis
Issue
Shortage of qualified practitioners ensuring development and
implementation of safeguarding frameworks & measures
Effects
Causes
Loss of cultural diversity
Intercultural dialogue
diminished
Social inclusion and
cohesion endangered
/Community sense of identity
and continuity jeopardized
Fail to develop ICH as a catalyst
for sustainable development
Lack of communities
involvement/ownership
Limited capacities of practitioners to
develop/implement frameworks
Lack of research and
networking
Decreasing inter-generational
dialogue
Lack of appropriate
policies
Notes: Will depend on following criteria:
Results chain, which is the most relevant issue to attain result
Which to do first or in parallel
Risks/assumptions
Resources

## Slide 13: Results Formulation of results to be attained
BSP: 36 C/5
What do you think of the following statements:
National capacities strengthened to develop and implement policies for intangible cultural heritage
Member States supported in building technical and institutional capacities and improving mechanisms to safeguard intangible cultural heritage at the national, regional and global levels
Communities assisted in engaging in safeguarding intangible cultural heritage
Notes: 13
Capacity-building projects under this strategy support the revision of policies and legislation, the redesign of the institutional infrastructure to cater to the needs of intangible cultural heritage safeguarding, the development of inventory methods and systems, the involvement of all stakeholders and the enhancement of knowledge and skills required to request international assistance or submit nominations to the Convention’s lists
Inventories
Safeguarding frameworks, plans and measures
National Policies
Integrate intangible cultural heritage into school curricula so as to make school education more culturally relevant to students
Periodic reporting allows States Parties to assess their implementation of the Convention, evaluate their capacities for safeguarding intangible cultural heritage, report on their inventories of intangible cultural heritage and update the status of elements inscribed on the Representative List

## Slide 14: Result Formulation of results to be attained
BSP: 36 C/5
A result = a concrete, visible and measurable change in state, induced by an intervention.
  It focuses on the direct target groups
  It captures the change among the target groups
  It illustrates what the target groups will do differently after the Organization’s action
  It can be formulated in the past or present tense
  It has to be “SMART”
Notes: 14

## Slide 15: Results versus outputs/deliverables Formulation of results to be attained
BSP: 36 C/5
A result is not an output/deliverable
An output/deliverable = the first effect of the intervention which contributes to the attainment of results. It reflects the action of the Organization.
  It reflects the achieved action of the Organization
  It can be tangible or intangible
  It is formulated in the past tense
Notes: 15

## Slide 16: Results versus outputs/deliverables Formulation of results to be attained
BSP: 36 C/5
Link between outputs/deliverables and results
The use of newly acquired knowledge and skills (outputs/deliverables) by the intended beneficiaries is often what leads to the change in situation – the result.
National authority, in collaboration with the local communities, establish an inventory on
intangible cultural heritage in the country X
- Assistance provided to the consultation process for coordinating the inventory
- Technical assistance provided for the formulation of the inventory
The country X ratifies the 2003 Convention and revises accordingly policies and legal frameworks
- Assistance provided to facilitate the ratification of the 2003 Convention
- Meetings have been organized in order to identify the needs for revising policies and legal framework to reinforce the implementation of the 2003 Convention
Local authorities in provinces Y and Z are implementing the safeguarding framework
- Awareness raised among local authorities on the safeguarding framework
- Challenges encountered in implementing safeguarding framework
Notes: 16

## Slide 17: Results framework/chain
BSP: 36 C/5
Results Outcomes Impact
Impact
Outcomes
Results
Global UNESCO results Matrix/framework
Activity/Project results chain/framework
Local authorities in provinces Y and Z are implementing the safeguarding framework
Intangible cultural heritage national legislative and administrative safeguarding frameworks developed and implemented

## Slide 18: Results Formulation of results to be attained
BSP: 36 C/5
Challenges in results formulation: Can all results be SMART?
- Different nature of results (C/4, C/5, global, regional, national)
At the ICH level, a result:
  Captures the variety of situations in the different regions
  Is aggregated to enable the contribution of the workplan level
  Identifies the direct beneficiaries/target group with a focus on the change
  Induces a shared responsibility by illustrating what the target groups will do differently after the Organization’s action
  Can be formulated in the past or present tense
  Has to be “SMART”, which can prove challenging
Notes: 18

## Slide 19: Results Formulation of results to be attained
Formulation of results need to be SMART:
Specific: It needs to express the nature of the change expected
Measurable: The level of attainment can be measured with qualitative or quantitative characteristics
Achievable: It has to be realistic with the human and financial resources available
Relevant: It has to contribute to the attainment of the higher level results and respond to the identified needs
Time-bound: Achievable within a specific timeframe

## Slide 20: Results Planning for monitoring of results
BSP: 36 C/5
Result: A concrete, visible and measurable change in state, induced by the intervention |  | 
Performance indicator: Parameter used to assess and measure the progress related to an expected result or an aspect of it. |  | 
Quantitative and/or qualitative Target/Benchmark: verifiable standard to be achieved at the end of the biennium.
Baseline: the starting point from which progress towards expected results will be measured through the use of performance indicators.
Means of verification:
The data sources and methodologies used to measure and analyse performance.
Notes: 20

## Slide 21: Results Planning for monitoring of results
BSP: 36 C/5
Result: Local authorities in province Y and Z are implementing the safeguarding framework |  | 
PI: % of recommendations in the framework implemented by local authorities |  | 
Target/Benchmark: 50 %
2-3 criteria to assess how well it is implemented
Baseline: (10%)
Means of verification:
Annual Reports on the implementation
Aggregation from workplans outputs/deliverables & results to C/5 outputs/deliverables & results
Notes: 21

## Slide 22: Results Formulation of performance indicators
BSP: 36 C/5
% of recommendations in the framework implemented by local authorities. Target/Benchmark: 50%, 10 most important. Baseline: 10%.
Remember useful performance indicators and associated target/benchmark are more important than they be perfect on paper!
Method and technique of
collection and analysis?
Stakeholders* concerned
and involved ?
Frequency of data
collection?
Data sources – how
to obtain information?
* e.g. Other UNESCO Services/Sectors, UIS, UN volunteers, women or youth organisations, NGOs, Category 2 Institutes
Notes: 22

## Slide 23: Results Formulation of performance indicators
BSP: 36 C/5
Measurement | Do | Don’t
To demonstrate that the local authorities implement the framework
% of recommendations in the framework implemented by local authorities in province Y and Z
The N° of meetings held by UNESCO to which local authorities are attending
To stress that monitoring mechanisms are put in place to ensure the smooth implementation of the framework
Number of corrective measures put in place to overcome the challenges encountered or Monitoring mechanism established by local authorities
Monitoring mechanisms document provided by UNESCO experts
Local authorities in province Y and Z are implementing the safeguarding framework
Notes: 23

## Slide 24: Planning for Monitoring
BSP: 36 C/5
 | Data Source | Method | Frequency | Stakeholders (responsibility)
Measuring results against performance indicators and benchmarks |  |  |  | 
50 % of priorities highlighted in the safeguarding framework addressed by ICH practitioners (Baseline: 10%) | Action plan and management procedures and reports by ICH practitioners | Qualitative analysis on the progress achieved against the commitments made in the framework | 1 phase: outcome of the workshop 2 phase: follow-up meetings organized at least yearly to discuss the progress achieved | Cat. 2 in collaboration with UNESCO CLT will coordinate with the concerned stakeholder (practitioners, national authorities, community members)
Measuring performance of the process and the pertinence of the deliverables (interventions and outputs) |  |  |  | 
Quality of the technical assistance provided | Feedback provided by concerned stakeholder during and preceding meetings | Analytical assessment of the feedback received | During the follow-up meeting, ensure agenda item on the satisfaction of the different stakeholders of the process | Cat. 2 in charge of collecting and managing the feedback received and report back to CLT on challenges and successes in order to benefit from the lessons learnt in future programme development
Notes: 24

## Slide 25: Results Formulation of results to be attained
BSP: 36 C/5
National capacities strengthened to develop and implement policies for intangible cultural heritage
  Performance Indicator:
  N° of countries supported by Cat. 2 in developing and/or revising and implementing ICH policies
Member States develop and implement policies for intangible cultural heritage
  Performance Indicator:
  N° of supported countries by Cat. 2 developed and/or revised and implemented ICH policies
Notes: 25

## Slide 26: Example of a results framework when programming
BSP: 36 C/5
Contribution of results achievements to Category 2 Institute Expected Result (and associated PI)
Notes: Results chain or framework at workplan level than contribution to Category 2 Institute result
Results matrix or framework at the Category 2 Institute level than contribution to ICH result

## Slide 27: Programming framework: Recap
BSP: 36 C/5
Where do you stand?
  Identification of the contribution to upstream result(s) (a prerequisite)
Where do you start?
  Assessment of the issues to be addressed
  Identification of stakeholders involved and concerned
  Estimation of resources available
What are you going to achieve?
  Formulation of results to be attained
  Definition of measurable indicators
How are you going to proceed?
  Development of a strategy for implementation and attainment of results
Notes: 27

## Slide 28: Correction of the Brain teaser
BSP: 36 C/5
B2. Increasing opportunities for quality basic education for children through community learning centres.
Statement | Intervention | Output /deliverable | Result | Performance indicator
A |  |  |  | 
B |  |  |  | 
C |  |  |  | 
D |  |  |  | 
E |  |  |  | 
F |  |  |  | 
G |  |  |  | 
H |  |  |  | 
I |  |  |  | 
J |  |  |  | 
K |  |  |  | 
X
X
X
X
X
X
X
X
X
X
X

## Slide 29
A
B
Situation analysis
Expected results
Implementation strategy
Implementation strategy explains how to move from the current situation to the one described in the result statement.
Set the context
(Issues and baseline)
Key outputs* (follow-up measures) leading to results and long-term vision
Conclusions of risk analysis
Linkage to other activities or projects?
Exit or transition strategy
Stakeholders (roles and responsibilities)
* Deliverables

## Slide 30: Balance among the three “R”s
Results
Resources
Reach*
* The geographical scope and aim, breadth and depth of influence and cooperation with stakeholders
BSP: 36 C/5

## Slide 31: 37 C/4 and C/5 UNESCO Programme Management Framework
BSP: 36 C/5
  - 8 Years timeframe for C/4 Strategic Objectives
  - 4 Years timeframe for C/5 Programme & workplans, expected results (ERs) and key outputs/deliverables.
    C/5 ERs: Targets/Benchmarks associated to Performance indicators are set for 2017
    Workplan ERs: Targets/Benchmarks associated to Performance indicators are set for 2015 & 2017
  - 2 Years timeframe for Regular Programme Budget
C/4 Medium-Term Strategy (8 years)
C/5 Programme (4 years) & Budget (2 years)
Workplans (Results: 4 years; Budget: 2 years)
Notes: 31
1. UNESCO’s official key programming documents are prepared in line with the Results-Based Management approach, the principles of the delegated Authority and Accountability, the reinforcement of Field Office network policy and progressively Results-Based Budgeting (RBB).
2. The Medium-Term Strategy, the C/4, represents one of the programmatic pillar of UNESCO. It sets out the strategic vision and overall programmatic framework and direction for UNESCO’s actions over eight years. The 37 C/4 is conceived as a rolling strategy (i.e. it can be revised every two years to take into account UN Reform, development in international/regional contexts, results attained and evaluations). It follows a programme-based approach (content overrides administrative structure), all UNESCO action will be driven by and organised around specific and complex global challenges and problems, calling for a mobilization of all UNESCO’s core competencies.
3. The 37 C/4 is translated into 2 C/5s, or Programme and Budget the other programmatic document, which is prepared on the basis on the Medium-Term Strategy. It serves as a framework for the quadrennial programming of UNESCO activities ensuring that the strategic objectives - including UNESCO Specific Priorities (e.g. Priority Africa, Priority Gender Equality), and Specific interventions in favour of priority groups and groups of countries (Youth, Least Developed Countries and Small Island Developing States), as well as other specific strategies - are duly taken into account at all stages of programme elaboration.
4. In parallel of each C/5 Programme: quadrennial workplans are elaborated.
5. The C/5 and workplans Programme, that is the substantive information and in particular the Implementation Strategy and expected results (ERs) are defined for a four years period, whereas the RP budgets are defined biennially. Hence, within the 37 C/4, there are 2 C/5s (i.e. 37 & 39) and workplans Programme and 4 RP budgets (i.e. 37, 38, 39 & 40).
- At C/5 level the targets/benchmarks associated to the performance indicators of ERs are set for 2017.
- At Workplans level the targets/benchmarks associated to the performance indicators of ERs are set for 2015 & 2017.

## Slide 32: 37 C/4 and C/5 Continued
Points to emphasize to advance further the RBM agenda:
- Rationale of the Intervention logic when programming and monitoring:
Why & How key outputs/deliverables will lead to workplan expected results and thereafter Why & How the latter will contribute to C/5 expected result and in turn Why & How the latter will contribute to C/4 Strategic Objective
Outputs/deliverables:
e.g. “Awareness raised among local authorities on the safeguarding framework” or “Capacities built to develop safeguarding framework”
Workplan Result:
e.g. “Local authorities in provinces Y and Z implement the safeguarding framework”
C/5 Result:
e.g. “The intangible cultural heritage including indigenous and endangered languages safeguarded”
C/4 Strategic Objective:
e.g. “Protecting, promoting and transmitting heritage”
Results framework including performance indicators and associated baseline and quantitative & qualitative targets/benchmarks for results and key outputs/deliverables.
Aggregation review mechanism from workplans to C/5 for both key outputs/deliverables and results (through performance indicators and associated quantitative and/or qualitative targets/benchmark).
Improving accountability: Formalize further the link of individual performance on outputs/tasks to programme/activity/project result achievements.
BSP: 36 C/5

## Slide 33: From programming to implementation
Programming period
Validation cycle
Approval by the DG
Budget released
Implementation period

## Slide 34
BSP: 36 C/5
Implementation
Notes: 34

## Slide 35: Monitoring implementation
Monitoring:
“A continuing function that uses systematic collection of data on specified indicators to provide management and the main stakeholders of an ongoing […] intervention with indications of the extent of progress and achievement of objectives and progress in the use of allocated funds.” OECD/DAC RBM Glossary - 2002.
Assessing progress, comparing the planned with the actual situation & making necessary changes if needed.
A
B
C
Situation analysis
Expected results
Actual situation and achievements
Implementation strategy
Results chain (C/4 to C/5 to Workplans)
Planned versus actual

## Slide 36: Monitoring implementation
Monitor progress achieved against:
Results
Assessing achievements against performance indicators and associated targets/benchmarks & baselines
Do the outputs/deliverables contribute to the attainment of results? If so, how?
Stakeholders and geographical scope
Assessing the contribution and involvement of stakeholders (beneficiaries and partners).
Does the benefit cover the expected geographical area?
Resources
Assessing the expenditures and human resources involved.

## Slide 37: Monitoring implementation Planned versus Actual
BSP: 36 C/5
Implementation strategy |  |  | 
Interventions | Outputs | Stakeholders | Actual
Providing technical assistance and support to Country A to enhance the effective safeguarding of ICH X | Workshop held for concerned stakeholders to identify and prioritize the key issues to be addressed and adopt framework | National authorities, ICH practitioners, concerned community members, Category 2 Institute actively engaged in the process | Workshop was held. It proved to be a fruitful exchange of experience and concern from the different concerned stakeholders. 15 recommendations were identified and 5 were underlined as urgent priority areas for intervention. The framework is still in its finalization phase and is expected to be adopted by the end of the month.
Expected Result ICH practitioners start to implement the safeguarding framework adopted with support from National authorities |  |  | 
Performance indicator(s) | Means of verification | Programmed benchmark | Actual
% of priorities highlighted in the safeguarding framework addressed by ICH practitioners | Qualitative analysis of management procedures in place and reports by ICH practitioners | Target: 50 % (Baseline: 10 %) | As the safeguarding framework is still in drafting phase it is too early at this point to report on results. However the workshop held contributed to sensitizing ICH practitioners on the crucial needs for improved safeguarding. This is expected to contribute to the successful implementation of the safeguarding framework .
Notes: 37

## Slide 38: Monitoring implementation
BSP: 36 C/5
Why invest resources in monitoring*?
It informs management on the assessment of the
implementation
It informs reporting on progress achieved towards the attainment of intended results to concerned stakeholders including the management of the Organization. Aim at evidence-based Result- oriented reporting.
* As a general rule of thumb, about 5% of the resources should be set aside for this purpose

## Slide 39: Monitoring implementation
Monitoring informs management
Documentation and assessment of the performance and progress achieved will allow you to answer the question:
“Is the implementation on track?”:
Yes: the information demonstrates that the assumptions of your programming framework remain valid and that implementation can continue as planned.
No: the information allows you to take informed decision on the onwards management of the implementation - what adjustments would be required? Adapting the implementation or reprogramming the results?
YES
NO
Notes: - External factors (represents unknown risks +/-)
- To what extent can we distinguish the achievements of the Organization and the influence of the external environment?
- Importance of analytical reporting

## Slide 40: Reprogramming Reviewing the planned results
When to reprogramme*?
If the assumptions of the programming framework are not valid or if an event or change of situation hinders the attainment of the expected result, it may be necessary to redefine the result and its relation to higher-level results (results chain).
Examples: A natural catastrophe; a new decentralized activity; a management decision to address other or new priorities.
Reprogramming is subject to validation from the Field Office Director and the upstream level
Accountability is associated to results thus when the expected results or results chain change, validation is required to ensure agreement on the change and to retain overall programme coherence.

## Slide 41
Example of a results framework when monitoring
BSP: 36 C/5
Contribution of results achievements to Category 2 Institute Expected Result attainment (and associated information)
Notes: Results chain or framework at workplan level than contribution to Category 2 Institute result
Results matrix or framework at the Category 2 Institute level than contribution to ICH result

## Slide 42: Reporting
Monitoring informs reporting
The information obtained through systematic monitoring informs
concerned stakeholders on the progress achieved, challenges and lessons learnt through reporting.
Reporting accounts for the resources entrusted in the Organization in terms of results attained and informs the management of the Organisation including decision-making on corrective measures required and future programme development.
Planning and programming
Monitoring and Reporting
Notes: On that basis supervisors will be able to elaborate the overall progress assessment of the MLA under your supervision.

## Slide 43: Reporting
Notes: Presentation of our statutory reporting and EX/4 Memo
Any questions on the Memo, who read it before?
Difference between written and on-line version on SISTER and BSP Internet site?
GE and AFR done by them based on the infor in SISTER… Difference GE/AFR in workplan and GE/AFR MP ERs
Need also contribution to OOs/SOs EOs and IADGs knowing that in the 37 C/4 will need to have contribution to SO and IADGs…

## Slide 44: Evaluation
A process that assesses in a systematic and objective manner the achievements of results in the light of the relevance, efficiency, effectiveness, impact and sustainability of on-going and completed activities, projects and programmes.
It is about: Learning from successful and less successful activities; Improving programme delivery, policy development and decision-making processes; enhancing accountability for the resources entrusted.
Key questions: are we doing the right things, are we doing it right and are there better ways of achieving the results?
3 Types of evaluations: Ex-Ante, Mid-Term, Ex-Post.
* As a general rule of thumb, about 1% of the resources should be set aside for this purpose

## Slide 45
Do not hesitate to contact:
Othilie du Souich at 8-13-37 or at o.du-souich@unesco.org
All training materials and documentation are available on the http://www.unesco.org/bsp

## Slide 46
Resource slides

## Slide 47
BSP: 36 C/5
Performance indicators must be measurable and data should be available over the duration of the intervention. Six criteria can be used to test the relevance of an indicator:
Validity: does it measure what it is intended?
Reliability: is it a consistent measure over time?
Sensitivity: when situation changes will it be sensitive to those changes?
Simplicity: will it be easy to collect and analyse the information?
Utility: will the information be useful for decision-making and learning?
Affordability: is it cost-effective?
Performance Indicators
Notes: 47

## Slide 48
BSP: 36 C/5
Baseline and Targets/Benchmarks
Baseline
Where we were
Target/
Benchmark Where we wanted to be
Measurement at a given point in time Where we actually are
Commitment
Performance
Notes: 48