| Agenda 1 | Annual Work Plan and Budget Plan for 2015 |
| --- | --- |

[Overview] Work Plan and Budget of 2015

(Unit: million KRW)

| Categories |  | Activities | Sub-activities | Budget |
| --- | --- | --- | --- | --- |
| 1. Building ICH Information System in the Asia-Pacific Region |  | 1.1 Collecting and Archiving ICH Information in the Asia-Pacific Region | - Collecting information on the current status of ICH safeguarding and upgrading and archiving the collected information | 100 |
|  |  | 1.2 Supporting ICH Information System Establishment in Central Asia | - Developing and operating an ICH website in Central Asia and publishing an ICH list brochure in Central Asia | 100 |
|  |  | 1.3 Producing an ICH Video Documentation | - Producing an ICH Video Documentation and encouraging collaborative works among documenting workers | 50 |
|  |  | Subtotal |  | 250 |
| 2. Strengthening Cooperative Networks for ICH |  | 2.1 Cooperation with UNESCO | - Participating in ICH-related meetings hosted by UNESCO, C2 Centres, Member States - Preparing UNESCO’s evaluation on ICHCAP’s activities for the renewal of its status as a C2 Centre | 60 |
|  |  | 2.2 Enhancing Asia-Pacific ICH Network | - Organizing a 2015 sub-regional meeting in Northeast Asia - Developing collaborative agenda on the sub-regional level - Organizing an ICH symposium - Implementing personnel exchange program - Preparing to develop ICH stakeholders network map and directory | 155 |
|  |  | 2.3 The 6th Governing Board Meeting and Media Cooperation | - Organizing and operating governing board meeting - Cooperating with media and other ICH organizations in Korea | 40 |
|  |  | Subtotal |  | 255 |
| 3. Promoting ICH and Raising Visibility |  | 3.1 Cooperation for Disseminating Pacific ICH Information | - Supporting promotional events for the publication - Holding the fifth Sub-regional Meeting in the Pacific - Surveying the current status of analogue data for restoration and digitization | 95 |
|  |  | 3.2 Publication of Newsletter and ICH Book | - Publishing and distributing ICH Courier - Korean publication of ICH Best Practices originally published by UNESCO | 65 |
|  |  | 3.3 Restoration and Digitization of ICH Data | - Selecting ICH data in need of digitization - Holding a digitization workshop - Publishing promotional material using the restored data | 50 |
|  |  | 3.4 Developing and Distributing ICH-Related Digital Contents | - Producing digital contents introducing UNESCO children’s books introducing ICH | 30 |
|  |  | Subtotal |  | 240 |
| 4. Construction of ICH Database and Archives |  | 4.1 Establishing Database for ICH Information in the Asia-Pacific Region | - Establishing a database of ICH information in the Asia-Pacific region | 60 |
|  |  | 4.2 Upgrade Server and Equipment | - Upgrading ICHCAP’s server | 100 |
|  |  | Subtotal |  | 160 |
| 5. Operating Cost | -Labor Cost |  |  | 1,222 |
|  | -Management Cost |  |  | 254 |
| Subtotal |  |  |  | 1,476 |
| Total |  |  |  | 2,381 |

1.	Building ICH Information System in the Asia-Pacific

2015 Project Focus Points (Information) - Lay groundwork for Collecting and archiving ICH information in the Asia-Pacific region - Develop environment for supporting ICH information system establishment in Central Asia - Strengthen ICH video documentation networks in the Asia-Pacific region

1.1 Collecting and Archiving ICH Information in the Asia-Pacific Region

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [article 7.2.(b)]

- Purpose: To collect basic ICH-related information in the Asia-Pacific region and to distribute to relevant institutions and the public as well as use the information for the projects of the Centre

- Target: 48 Member States in the Asia-Pacific region

- Contents:

- Collecting basic information related to ICH safeguarding efforts in the Asia-Pacific region (two countries)

- Updating and supplementing the collected information from 2009 to 2011 (three countries)

- Archiving the collected information from 2009 to 2014 and providing the information online (two sub-regions)

- Supporting Bodies: Governments, ICH-related institutions, experts, and communities

- Budget: KRW 100 million

| Performance Indicators | Benchmark |
| --- | --- |
| - Collect and update ICH-related information of five countries (new: 2 countries; update: 3 countries) - Provide information online | - Make reports on more than three countries - Post information including documents and visual materials on more than two sub-regions |

- Expected Results

[Reference:  ICH Information in the Asia-Pacific Region]

Previous Progress

| Year | Number of Country | Name of Country | Results |
| --- | --- | --- | --- |
| 2009 | 6 | Cambodia, Fiji, Mongolia, Thailand, Uzbekistan, and Vietnam | - Project reports on six countries (more than 100 pages each) - 370 Photographs - Video clips |
| 2010 | 7 | Bangladesh, Bhutan, Indonesia, Nepal, Philippines, Papua New Guinea, and Tajikistan | - Project reports on seven countries - 500 Photographs - Video clips |
| 2011 | 7 | Cook Islands, Laos, Kyrgyzstan, Marshall Islands, Pakistan, Sri Lanka, and Tonga | - Project reports on seven countries - 290 Photographs - Video clips |
| 2012 | 5 | Myanmar, Kazakhstan, Palau, Vanuatu, and Iran | - Project reports on five countries - 270 Photographs - Video clips |
| 2013 | 5 | Turkey, Japan, India, Federated States of Micronesia, and the Republic of Korea | - Project reports on five countries - 270 Photographs - Video clips - Summary of the reports of four sub-regions (25 countries) - Analysis of the reports of four sub-regions (16 countries) |
| 2014 | 5 (ongoing) | Solomon Islands, People’s Republic of China, Uzbekistan(2nd phase), Tajikistan(2nd phase), and Thailand(2nd phase) | - Project reports on five countries - Photographs - Video clips |
| Total | 35 |  |  |

Future Plan

- Collect basic ICH-related information of forty countries in the Asia-Pacific region by 2016 (collected the information of thirty two countries (67%) by 2014 among forty-eight Member States in the region)

- Upload the project reports and visual materials from 2009 to 2014 to ICHCAP website

1.2 Supporting ICH Information System Establishment in Central Asia

- Grounds: Agreement between the Government of the Republic of Korea and        UNESCO [Article 7.2 (b)]

- Purpose: To build foundations for ICH information systems and to help implement the 2003 Convention in Central Asian region

- Target: Member States in Central Asia (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan, and Uzbekistan)

- Contents:

- Publishing an ICH list brochure in Central Asia

- Developing and operating ICH website in Central Asia

- Organizing the sub-regional network meeting on the safeguarding of ICH

- Organizing Bodies

- Governmental organizations and specialized institutions on ICH in each country

- Budget: KRW 100 million

- Expected Results

| Performance Indicators | Benchmark |
| --- | --- |
| - Foundation for an ICH information system in Central Asia developed - Participation of Member States in Central Asia ensured | - Agreement on a collaborative project for building the foundation for ICH information systems (more than two countries) - At least one expert from each country |

[Reference: ICH Information System in Central Asian Region]

Previous Progress

| Year | Project activities | Results |
| --- | --- | --- |
| 2010 | - Held the First Central Asia Sub-regional Network Meeting for ICH Safeguarding (March, Uzbekistan) | - Thirty experts from four Central Asian countries participated - Action plan (Central Asia and ICHCAP: Partnership for Sustainable ICH Safeguarding) adopted |
| 2011 | - Held the Second Central Asia Sub-regional Network Meeting on the Safeguarding of ICH (July, Tajikistan) | - Thirty experts from four Central Asian countries participated - Action Plan and the Guideline on the Implementation of the Project for 2011 to 2014 |
|  | - Launched the first phase of the three-year project, Facilitating ICH Inventory Making and Using Online Tools for ICH Safeguarding in the Central Asian Region (Project activities: creating a special committee for the project implementation and preparing the preliminary list of ICH by organizing the existing information) | - Signed the agreement on the first phase project by the four countries (Kazakhstan, Kyrgyzstan, Tajikistan and Uzbekistan) |
| 2012 | - Held the Third Central Asia Sub-regional Network Meeting on the Safeguarding of ICH (May, Kyrgyzstan) | - Thirty experts from four Central Asian countries participated - 2012 Action Plan for Execution of the Second Phase of the Project adopted |
|  | - Implemented the first phase of the three-year project (By July) - Launched the second phase of the three-year project [Project activities: conducting onsite survey (collecting information on ICH elements); developing a model ICH online database system] | - First phase of the project completed [Special committees for the project (four countries); preliminary ICH lists ( four countries); questionnaires for onsite surveys (four countries)] - Signed the agreement on the second phase project by the four countries |
| 2013 | - Held the Fourth Central Asia Sub-regional Network Meeting on the Safeguarding of ICH (May, Kazakhstan) | - Thirty experts from four Central Asian countries participated - 2013 Action Plan for Execution of the Third Phase of the Project adopted |
|  | - Implemented the second phase of the three-year project (Until July) - Launched the second phase of the three-year project (Project activities: Establishing a system for operating an ICH database by the respective countries; preparing to create national website on ICH to enhance visibility; and preparing drafts to publish an ICH inventory brochure) | - Second phase of the project completed [More than one onsite survey conducted by each country; one model online database system established and distributed] - Signed the agreement on the Third phase project by the four countries |
| 2014 | - Held the Fifth Central Asia Sub-regional Network Meeting on the Safeguarding of ICH (September, Uzbekistan) | - Sixty experts from five Central Asian countries (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan), Mongolia and the Republic of Korea participated - Evaluated the three-year project and discussed development of the future cooperative projects (Decision: complete the website creation and brochure publication in 2015) |
|  | - Implemented the first phase of the three-year project (Until November) | - Third phase of the project will be completed [Four draft websites on ICH developed; four draft manuscripts for ICH inventory booklet (brochure) prepared] |

Future Direction

- Develop follow-up projects for enhancing visibility of the first three-year project (2015-2016)

- Publish an ICH related booklet in Central Asia

- Develop and operate an ICH website in Central Asia

- Discuss the second three-year project on Supporting ICH Information System Establishment in Central Asia (2016-2018)

1.3 Producing an ICH Video Documentation

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [article 7.2.(b)]

- Purpose: To raise awareness and activate activities for the public by producing a professionally documented video that promotes ICH visibility in the Asia-Pacific region

- Target: Uzbekistan (Tentative)

- Contents: Producing an ICH video documentation and encouraging collaborative works among the concerned community and filming experts

- Organizing Bodies: Academy of Sciences of the Republic of Uzbekistan, International Institute for Central Asian Studies (IICAS)

- Budget:  KRW 50million (External resources shall be secured tentatively)

- Expected Results

| Performance Indicators | Benchmark |
| --- | --- |
| - To share ICH documentation techniques - To conduct a joint documentation project | - At least one expert meeting among filming experts - At least one ICH element documented |

[Reference:  ICH Video Documentation]

Previous Progress

| Year | Country | Elements | Co-organizers |
| --- | --- | --- | --- |
| 2012 | Vietnam | - Ca tru singing (20 min) - Water puppetry (45 min) - Cap sac ritual (45 min) | - Vietnam Institute for Musicology |
| 2013 | Mongolia | - Nadam festival (30 min) - Shaman ritual in Mongolia (30 min) | - Foundation for the Protection of Natural and Cultural Heritage |
| 2014 | Kyrgyzstan | - Manas epics | - Kyrgyzstan National Commission for UNESCO, and the Institute of Literature and Language of the National Academy of Science |
| 2015 | Uzbekistan | - Not Determined | - Academy of Sciences of the Republic of Uzbekistan, International Institute for Central Asian Studies (IICAS) |

Future Plan

- Expand target countries and ICH elements by continuing the project

- Strengthen networks and information sharing for ICH documentation by organizing the meetings

2. Strengthening Cooperative Networks for ICH

2015 Project Focus Points (Networking) - Lay groundwork for collecting and archiving ICH information in the Asia-Pacific region - Develop environment for supporting ICH information system establishment in Central Asia - Strengthen ICH video documentation networks in the Asia-Pacific region

2.1 Cooperation with UNESCO

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [article 7.2.(d)]

- Purpose

- To strengthen cooperation mechanisms with UNESCO, C2 Centres, and Members States

- To contribute to UNESCO’s global strategy

- To support ICHCAP’s evaluation and renewal process

- Contents

- Participating in UNESCO-related conferences (Intergovernmental Committee, General Conference, etc.)

- Participating in meetings organized by C2 Centres and other relevant institutes of Member States

- Preparing UNESCO’s evaluation on ICHCAP’s activities for the renewal of its status as a C2 Centre

- Budget: KRW 60 million

- Expected Results

| Performance Indicators | Benchmark |
| --- | --- |
| - Participation in a number of meetings organized by UNESCO, C2 Centres, and Member States - Efficient support for UNESCO’s evaluation on ICHCAP | - Three UNESCO meetings (intergovernmental committee, Global C2 Centres, etc.) - Two C2 Centre meetings (Governing boarding meetings of C2 Centres in Japan and China) - Three ICH meetings or conferences organized by Member States - Efficient communication with UNESCO and arrangement for evaluation process and preparation of all documents |

2.2 Enhancing Asia-Pacific ICH Network

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [article 7.2. (c)]

- Purpose

- To strengthen sub-regional cooperation through cooperative projects regarding ICH safeguarding in the Asia-Pacific region

- To enhance cooperative networks with ICH stakeholders in Asia-Pacific by exchanging experiences, information, and knowledge on ICH

- Contents

- Organizing a 2015 sub-regional network meeting in Northeast Asia and develop collaborative agenda on the sub-regional levels of Southeast Asia and South Asia

- Organizing an ICH symposium in Korea in collaboration with ICH-related academic society to understand and spread the spirit and contents of the 2003 Convention

- Implementing a personnel exchange program with Member States

- Preparing a two-year plan for ICH stakeholders network map and directory

- Budget: KRW 155 million

- Expected Results

| Performance Indicators | Benchmark |
| --- | --- |
| - Organize 2015 Northeast Asian sub-regional meeting - Develop collaborative agenda in Southeast Asia and South Asia - Organize an ICH Symposium - Organize national personnel exchange program - Develop an ICH network directory plan | - Participation of five countries (including DPRK) and drawing a tentative cooperative project - Two consultation meetings with UNSCO regional offices (Bangkok, Kathmandu) - Participation of more than fifty ICH experts - Invitation for two countries (policymakers, experts, NGOs, academics) - Three advisory and two working meetings |

- Direction for 2015

- Focus on developing sub-regional cooperation and network meetings in Northeast, Southeast, and South Asia in collaboration with UNESCO regional offices (Bangkok, Beijing and so on) instead of organizing international conferences

2.3 6th Governing Board Meeting and Media Cooperation

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [article 7.2.(d), 8.1-3]

- Purpose

- To discuss and decide matters related to the operation and work plan of ICHCAP

- To cooperate with the media and other organizations in Korea

- Target: Governing board members, media, and other ICH-relevant organizations

- Contents

- Reviewing the 2014 audit report and the Centre’s activities and program in 2015

- Deliberating and approving ICHCAP’s annual work plan and budget for 2016

- Press conference and cooperation with other ICH relevant organization

- Organizing Bodies: ICHCAP

- Budget: KRW 40 million

- Expected Results

| Performance Indicators | Benchmark |
| --- | --- |
| - Organize and operate 6th governing board meeting - Enhance media coverage - Strengthen cooperation with other ICH organizations in Korea | - Consultation with UNESCO at least one month before and distribute agenda to the directors three weeks prior to the meeting - Two press conferences and four interviews - Three consultation meetings with ICH relevant organizations for cooperation on ICHCAP’s activities |

3. Promoting ICH and Raising Visibility

2015 Project Focus Points (Visibility) - Publish books and up-to-date information on ICH - Develop cooperative projects on raising visibility of Pacific ICH - Develop and distribute ICH related digital contents to promote to the general public

3.1 Cooperation for Disseminating Pacific ICH Information

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [Article 7.2.(b)]

- Purpose: To strengthen the Pacific cooperative network through the joint project and to disseminate information on Pacific ICH

- Contents

- Supporting promotional events for the publication Traditional Knowledge and Wisdom: Themes from the Pacific Islands in the Pacific (Continued from Pacific publication project in 2014)

- Holding the Sixth Sub-regional Information and Networking Meeting for ICH in the Pacific

- Surveying the current status of analogue data on ICH and its needs in the Pacific for restoration and digitization

- Budget: KRW 95 million

- Expected Results

- Enhance ICH visibility though the information dissemination

| Performance Indicators | Benchmark |
| --- | --- |
| - Number of promotional events held in the region since the publication - Number of local and public attendees participating in the promotional events - Number and importance of ICH elements covered through the publication or report | - Each one event in six countries - Thirty locals in each event and 30 percent of youths of the overall attendees - Over five elements in a country chosen by local expert to be represented at the publication or report |

- Strengthening cooperative network among Pacific countries

| Performance Indicators | Benchmark |
| --- | --- |
| - Number and importance of institutions represented at the network meeting - Profile of representatives participating in the network meeting - Countries where the joint project has been implemented since the network meeting | - Five governmental institutions and five regional organizations - Decision makers, public officials, trainers, scholars - Three countries each making MOUs in implementing the joint projects |

[Reference: The Pacific Project]

- Flow of the Sub-regional Meetings in the Pacific

|  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015(tbd) |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1st Pacific Meeting | 2nd Pacific Meeting | 3rd Pacific Meeting | 4th Pacific Meeting | 5th Pacific Meeting | 6th Pacific Meeting |
| Hosting country | Fiji | Tonga | Cook Islands | Vanuatu | FSM | Palau |
| Participating countries | Representatives of 4 Pacific countries: Fiji, PNG, Tonga, Vanuatu | Cook Islands newly joined the network | Palau newly joined the network | FSM newly joined the network | Samoa newly joined the network | Fiji, FSM, Palau, PNG, Tonga, Vanuatu, Cook Islands, Samoa (8 countries) |
| Results | - Expanded the regional network among Pacific countries, UNESCO regional office, and ICHCAP - Shared information on country report of safeguarding ICH - Launched and carried out a joint project for promoting Pacific ICH |  |  |  |  |  |

- Flow and direction of the Pacific projects

| 2012 | 2013 | 2014 | 2015 | 2016 |
| --- | --- | --- | --- | --- |
| 3rd Pacific Meeting | 4th Pacific Meeting | 5th Pacific Meeting | 6th Pacific Meeting | 7th Pacific Meeting |
| - Focused on the first establishment of the network in the region - Agreed to enhance ICH visibility through information building and managing | -Resolved to implement the publication project | -Hold an editorial session for the publication | - Promote the result of the publication project | - Propose a new publication in series |
|  | - Launched with 6 countries | - Complete the publication (27 articles from 6 countries under 5 themes) | - Implement promotional events in the Pacific |  |
|  | Joint Publication Project(3years) |  |  |  |
|  |  | 5th Pacific Meeting | 6th Pacific Meeting |  |
|  |  | - Brought issues on managing analogue/digital data | - Resolve to launch the Project | - Implement digital restoration |
|  |  |  | -Survey the status of analogue data |  |
|  |  | Restoration and Digitization of ICH Data(3years) |  |  |

3.2 Publication of Newsletter and ICH Book

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [Article 7.2.(b)]

- Purpose: To disseminate information on ICH safeguarding issues and to promote safeguarding activities

- Contents:

- Publishing and distributing ICH Courier Vols. 23 to 26

- Korean publication of ICH Best Practices originally published by UNESCO

- Budget: KRW 65 million

- Expected Results

- Share recent information on ICH safeguarding with public and experts

| Performance Indicators | Benchmark |
| --- | --- |
| - Degree of newness of information - Number of copies distributed offline - Number of downloading and e-mailing online | - News and issues came up in a year - 2,000 copies offline quarterly - 1,000 e-mailings and downloads quarterly |

[Reference: List of Publication]

- Newsletter ICH Courier (Vol. 1-22) each in English and Korean

- UNESCO ICH leaflets (2010-2012) in Korean

- UNESCO ICH brochures (2008-2011) in Korean

- UNESCO ICH brochures (2010-2011) in English and French

- The Pacific ICH Information brochures in 2011 and 2013

- UNESCO ICH children books in Korean (2013)

- ICHCAP’s international conference reports (2009-2014)

3.3 Restoration and Digitization of ICH Data

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [Article 7.2.(a)]

- Purpose: To restore analogue ICH data and increase ICH information accessibility

- Contents: Selecting ICH data in need of digitization, holding a digitization workshop, supporting digitization of ICH data for selected country

- Budget: KRW 50 million

- Country: To be decided (Country selection is to be decided after consultation with UNESCO regional office considering urgency and efficiency)

- Expected Results

- Strengthen digitization capacity for ICH data in need of restoration

- Accumulate ICH data and raise accessibility to rare ICH information

| Performance Indicators | Benchmark |
| --- | --- |
| - Holding a digitization workshop - Number of digitized ICH data - Number of times used by individuals, groups, and organizations | - Once a year for experts and organizations in target countries - Restore ICH data over three hundred hours - Used over twenty times by target users |

- Future Plan or Use

- Focus on laying the groundwork for the construction of ICH database in long-term project

[Reference: Progress of Digital Restoration]

- Flow of the digital restoration projects

| 2011 | 2012 | 2013 | 2014 | 2015 |
| --- | --- | --- | --- | --- |
| - Hold the Expert Meeting - Launch the project | -Implement digital restoration(713 hours audio recordings) - Produced the Audio CD sets and distributed |  |  |  |
| Project in Mongolia |  |  |  |  |
|  |  | - Hold the Expert Meeting - Launch the project | -Digital restoration 300 analogue audio recordings |  |
|  |  | Project in Vietnam |  |  |
|  |  |  | - Launch the project | - Digital restoration (360 hours-audio data, 77 films) To be completed by May 2015 |
|  |  |  | Project in Uzbekistan |  |
|  |  |  |  | -Holding a workshop -Restoring old data |
|  |  |  |  | New Project |

3.4 Developing and Distributing ICH-Related Digital Contents

- Grounds: Agreement between the Government of the Republic of Korea and UNESCO [Article 7.2.(b)]

- Purpose: To raise public awareness, especially for younger generations, by developing and disseminating ICH-related digital contents

- Targets: Youth and Children

- Contents: Producing digital contents introducing UNESCO children’s books introducing ICH (Korean language, Using augmented reality method technology)

- Budget: KRW 30 million

- Expected Results

- Raise ICH awareness by arousing children’s interest

| Performance Indicators | Benchmark |
| --- | --- |
| - Number distributed to individuals, institutes, and organizations | - Distribute over two hundred sets |

- Future Plan or Use

- Secure potential social groups enjoying ICH by arousing their interest from an early age

[Reference]

- Production of ICH animation Magic Tour of World’s ICH (five episodes, 2013)

4. Construction of ICH Database and Archives

2015 Project Focus Points (Information) - Upgrade hardware (server and storage equipment) for stable information service - Expand ICH information database

4.1 Establishing Database for ICH Information in the Asia-Pacific Region

- Grounds: Information Strategic Planning (ISP)

- Purpose: To construct a database of ICH information using ICHCAP’s ICH information collection

- Targets: ICHCAP’s data

- UNESCO’s ICH elements (information and multimedia files for 269 elements in 97 countries)

- ICH information collected (30 publications, 230 multimedia files)

- Contents: Establishing a database of ICH information in the Asia-Pacific region

- Budget: KRW 60 million

- Database construction (text, video, audio information): KRW 45 million

- Operating expenses (expert consultation, travel expenses, etc.): KRW 15 million

- Expected Results

| Performance Indicators | Benchmark |
| --- | --- |
| - Increase amount of ICH data in database | - ICH database: information on UNESCO’s 269 elements |

4.2 Upgrading Server and Equipment

- Grounds: Information Strategic Planning (ISP)

- Purpose: To add and upgrade servers for entering ICH info and ICHCAP’s data

- Targets: Servers, storage, and network equipment

- Contents: ICHCAP’s server upgrades

- Budget: KRW 100 million

- Expected Results

| Performance Indicators | Benchmark |
| --- | --- |
| - Upgrade ICHCAP’s servers and equipment for better storage and use of ICH information at ICHCAP | - One server - One storage - One network device - One security device |