CONVENTION FOR THE SAFEGUARDING OF THE 
INTANGIBLE CULTURAL HERITAGE

INTERGOVERNMENTAL COMMITTEE FOR THE
SAFEGUARDING OF THE INTANTINGIBLE CULTURAL HERITAGE

Bureau meeting

UNESCO Headquarters, Room IV

25 October 2010, 10 a.m. to 1 p.m.

Report on the utilization of the funds allocated for ‘other functions of the Committee’ 
as authorized by decision 5.COM 1.BUR 6

- In its Decision 4.COM 12, the Committee set in place a mechanism for authorizing expenditures from the Intangible Cultural Heritage Fund allocated for ‘other functions of the Committee’. In paragraph 5 of that Decision, the Committee ‘delegates to its Bureau the authority to decide upon the utilization of the funds allocated under item 3 of the Plan, on the basis of specific proposals to be prepared by the Secretariat’. At its previous session on 27 November 2009, in its Decision 5.COM 1.BUR 6, the Bureau of the fifth session of the Committee authorized expenditures in the amount of US$61,976. Paragraph 4 of that decision requests the Secretariat to give a full financial report on the way the funds are spent on each project. The present document constitutes the report requested.

- Funds were allocated by the Bureau for three purposes:

- Workshop for NGOs (US$20,000);

- Publication of the Urgent Safeguarding List, Representative List and Register of programmes, projects and activities (US$30,000);

- Compiling information on measures and methodologies used or to be used in the selected programmes, projects and activities (US$11,976).

- Due to scheduling difficulties, it was not possible to confirm dates for the NGO workshop and execute a contract prior to the end of June 2010. The funds allocated for that purpose are included in the Plan for the use of the resources of the Intangible Cultural Heritage Fund that was adopted by the General Assembly in its third session (Resolution 3.GA 8).

- The Secretariat has now received a formal invitation from the Gabonese authorities and looks forward to finding a mutually agreeable time to organize an NGO workshop in 2011. Funds for that purpose are included within the spending plan that is the subject of Document ITH/10/5.COM 2 BUR/4.

- The Annex to the present document provides a financial report on the funds spent for items 2.b and 2.c above.

ANNEX

Financial report on the funds used under 
‘Other functions of the Committee’

| Activity 1: Workshop for NGOs Timeframe: Activity postponed to 2011 Total amount approved by the Bureau: US$20,000.00 |
| --- |
| Detailed activity implementation | Budget breakdown |
| Activity not implemented before June 2010. No expenditures were incurred for this activity | US$0.00 |

| Activity 2: Publication of the Urgent Safeguarding List, Representative List and Register of programmes, projects and activities Timeframe: December 2009 to June 2010 Total amount approved by the Bureau: US$30,000.00 |
| --- |
| Detailed activity implementation*: | Budget breakdown |
| An author’s contract was established for the drafting of 15 texts to be integrated in the brochures on the Urgent Safeguarding List and on the Register of Best Practices | US$3,313.72 |
| Contracts were established with the UNESCO Division of Conferences, Languages and Documents for the design, lay-out and printing of the 3 brochures on the Urgent Safeguarding list, Representative List, and the Register of Best Practices (2,000 copies in English and 1,300 in French) | US$22,063.19 |
| Contracts were established for the translation of the 3 brochures in English and French | US$2,914.98 |
| Total | US$28,291.89 |

*	In addition to the funds from the Intangible Cultural Heritage Fund, US$42,839 in UNESCO Regular Programme funds were used to produce these publications, for the total expenses of US$71,130.

| Activity 3: Compiling information on measures and methodologies used or to be used in the selected programmes, projects and activities Timeframe: 1 December 2009 to 31 December 2010 Total amount approved by the Bureau: US$11,976.00 |
| --- |
| Detailed activity implementation* | Budget breakdown |
| A Fee Contract was established with the Indonesian National Commission to carry out in collaboration with the Batik Museum in Pekalongan the following activities: | US$11,975.00 |
| Creation of a manual in English language describing the measures and methodologies used in the Batik Museum Education Programme | US$4,000.00 |
| Development and design of an exhibition, suitable to serve as a travelling exhibition, presenting the activities, experiences and methodologies used in the programme | US$4,000.00 |
| Preparation of two edited video programmes, with English sub-title, presenting the activities, experiences, measures and methodologies used in the programme | US$3,975.00 |

*	It is to be noted that the contract with the National Commission of Indonesia has a completion date of 31 December 2010. The second and last payments (respectively US$4,000 and US$3,975) are therefore pending.